## Sheet1
Milestone | Description
Function | The web interface works function-wise
Style | The UX is improved and stylized
Integration | Implemented with IIS and ActiveDirectory
Milestone | Date | Value
Function | 2021-11-18 | 0
| 2021-11-18 | 80
Style | 2022-01-14 | 0
| 2022-01-14 | 80
Integration | 2022-02-11 | 0
| 2022-02-11 | 80
Name | Description | Start Date | End Date | Duration
Create Rubrics | Add ability to create, edit, and delete rubrics for use in grading | 2021-10-01 | 2021-10-08 | 6
Create Reviews | Add ability for students to create review, and seniors to evaluate them | 2021-10-11 | 2021-10-15 | 5
Review Emails | Create and test sending emails for notifications related to reviews | 2021-10-16 | 2021-10-27 | 8
Homepage | Create page to view all reviews and create/accept ones as well | 2021-10-28 | 2021-11-03 | 5
Admin Section | Section to let instructor edit and manage data | 2021-11-04 | 2021-11-18 | 11
Forms | Standard forms are styled and laid out | 2021-11-22 | 2021-11-26 | 4
Rubric Creation | Rubric creation form stylized | 2021-11-29 | 2021-11-30 | 2
Rubric Grading | From for filling out rubrics stylized and improved | 2021-12-01 | 2021-12-03 | 2
Home Page | Home page stylized and improved | 2021-12-06 | 2021-12-17 | 10
Admin Section | Admin section stylized and improved | 2021-12-20 | 2022-01-10 | 5
Style review | Ensure all styles are uniform and Ux practices are upheld | 2022-01-11 | 2022-01-14 | 4
Hosted on IIS | Get the web interface hosted on IIS | 2022-01-17 | 2022-01-19 | 3
ActiveDirectory Auth | Integrate authentication in the website using LDAP | 2022-01-20 | 2022-02-11 | 17